## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2022-10-17 | 3 | Lunes, 7 de noviembre de 2022 | 20 | 2 | Ongoing | 2021-09-03 | Entrega Sprint 0 (Conformacion de equipo / Idea / Roles / Documentacion Preliminar) | 100%
Unplanned
Unplanned
Unplanned
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
1 | 2022-10-17 | 1 | 2022-10-17 | 6.5 | 7 | Released | 2022-10-25 | Desarrollar Product Backlook Priorizado | 1 | 7.692%
1 | 2022-10-18 | 0.28571 | 2022-10-17 06:51 | 1.8 | 2 | Released | 2021-09-10 | Construir Repositorio (Github) donde integraran el Trabajo | 1 | 11.11%
1 | 2022-10-18 06:51 | 0.42857 | 2022-10-17 17:09 | 2.8 | 3 | Ongoing | 2021-09-10 | Construir Archivo Gestion Configuracion | 1 | 7.143%
1 | 2022-10-18 17:09 | 0.42857 | 2022-10-18 03:26 | 2.7 | 3 | Ongoing | 2021-09-10 | Construir Historias de Usuario a desarrollar en Sprint No.1 | 1 | 11.11%
1 | 2022-10-19 03:26 | 1 | 2022-10-19 03:26 | 6.8 | 7 | Ongoing | 2021-09-10 | Creacion y configuracion cuenta Devops (SrumBoard y tareas) | 1 | 2.941%
Historias no asignadas |  |  |  | 0
Total |  |  |  | 20.6 | 22
|  |  |  | Estimadas | Reales
Formulas:
Start = IF(OR(C10="",[Incr.]=""),"",C10)
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Desarrollar Product Backlog Priorizado | Done | 3 | 0 | 1 | Documentacion | Se Desarrolla Product Backlog Priorizado
2 | Construir Repositorio (Github) donde integraran el Trabajo | Done | 8 | 0 | 1 | Documentacion | Se Construye Repositorio (Github) en Proyecto, El Proyecto tiene tres fases (To Do, In Progress, Done)
3 | Construir Archivo Gestion Configuracion | Done | 20 | 0 | 1 | Documentacion | Stack: MERN Front: React Back: JavaScript, Express, Node BD: Mongo
4 | Construir Historias de Usuario a desarrollar en Sprint No.1 | Ongoing | 1 | 0 | 1 | Documentacion | Construccion Historias de Usuario Sprint 1
5 | Creacion y configuracion cuenta Devops (SrumBoard y tareas) | Ongoing | 13 | 0 | 1 | Documentacion | Configuración inicial DevOps
Proyecto
Académica
Académica
Note on D3: ====== ID#AAAAO20iw4E Use the following statuses (2021-09-03 00:19:36) Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on E3: ====== ID#AAAAO20iw4I Petri Heiramo (2021-09-03 00:19:36) Story Points or Ideal Days
Note on F3: ====== ID#AAAAO20iw4A Petri Heiramo (2021-09-03 00:19:36) Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on G3: ====== ID#AAAAO20iw38 Petri Heiramo (2021-09-03 00:19:36) You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.